## Instructions
Using the Status tracker
At the end of each week, update the status of all activities completed during the week
The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week)
Fill in hours spent on each activity during the current week
If 5 team members each spent an hour, that counts as 5 hours
Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)
For new activities, identify the type of activity - documentation, coordination, estimation etc.
At the end of each week, plan ahead for the following week
Identify people responsible for each activity
Estimate the hours needed for the activity
PROJECT NUMBER | DASS-Team 21
PROJECT NAME | AI Video Journal Application (HopeLog)
PROJECT MENTOR (Client) | Mr Jazeel Jabbar
TEAM MEMBERS | Anshul Krishnadas Bhagwat
Raghav Doshi
Krishna Saketh Ayyagari
Ishaan Romil
Manasi Mundada

## Status
PROJECT NUMBER | DASS-Team 21
PROJECT NAME | AI Video Journal Application (HopeLog)
PROJECT MENTOR (Client) | Mr Jazeel Jabbar
Activity Name | Type | Responsible | Estimated Team Hours | Actual Hours | Status | Comments | Estimation error | Estimation error %
See Instructions sheet for usage
Week 1 (January 15- January 21)
Team Meeting | Coordination | Ishaan, Raghav |  | 1.5 | Done
Fix first client meeting | Coordination
Client meeting - 15th January | Coordination | Anshul |  | 1 | Done
Research existing technology | Preparation | Saketh | 2 | 1.5 | Done |  | 0.5 | 33.3333
Status tracker | Documentation | Saketh | 1 | 0.5 | Done |  | 0.5 | 100
Week 2 + Quiz Week (January 22 - January 28, January 29 - February 2)
Client Meeting - 22nd January | Coordination |  |  | 1 | Done
Team Meeting 1 - 23rd January | Coordination | Manasi | 1 | 1 | Done |  | 0 | 0
Team Meeting 2 - 24th January | Coordination | Anshul | 2 | 1 | Done |  | 1 | 100
Slack Setup | Preparation | Manasi | 2 | 1 | Done |  | 1 | 100
Advanced GitHub Familiarisation | Preparation | Ishaan | 1 | 1 | Done |  | 0 | 0
NodeJS and MongoDB learning | Preparation | Manasi | 4 | 2 | Done |  | 2 | 100
Responsive Frontend Landing Page (Figma) | Design | Saketh | 4 | 3.5 | Done |  | 0.5 | 14.2857
Preliminary LLM Integration Research | Preparation | Raghav | 4 | 3 | Done |  | 1 | 33.3333
Scrum Management Planning | Preparation | Anshul | 6 | 5 | Done |  | 1 | 20
Project Synopsis - due 25th January | Requirements |  | 2 | 1.5 | Done |  | 0.5 | 33.3333
Learning Video Integration | Preparation | Ishaan | 4 | 4 | Done
Project Plan - due 29th January | Documentation | Raghav | 2 | 2 | Done
Week 3 (February 2 - February 9)
Client Meeting - 3rd February | Coordination | Manasi |  |  | Delayed | Client Postponed the meeting
Team Meeting - 8th February - discussing project plan | Coordination | Anshul | 1 | 1 | Done |  | 0 | 0
Client Meeting - 8th February | Coordination | Anshul |  |  | Delayed | Client Postponed the meeting
Trello Familiarization | Preparation | Anshul | 3 | 3 | Done
Week 4 (February 10 - February 16)
Client Meeting - 11th February | Coordination | Manasi |  |  | Delayed | Client Postponed the meeting
Complete Course on Figma and React | Preparation | Saketh | 5 | 4 | Done |  | 1 | 25
Gemini LLM Deep Dive | Preparation | Raghav | 5 | 2 | Delayed
Learning Audio & Video Processing (via Ffmpeg, Librosa) | Preparation | Ishaan | 3 | 1 | Done
Learning functionality of TerraForm, Ansible, and Jenkins | Preparation | Ishaan | 2 | 2 | Done
Learn Encryption Techniques | Preparation | Manasi | 2 | 2 | Done
Requirement breakdown for 1st release | Preparation | Anshul | 2 | 2 | Done
Week 5 (February 17 - February 23)
SRS Document | Documentation | Anshul, Saketh | 3 | 3 | Done |  | 0 | 0
Client Meeting - 18th February | Coordination | Manasi | 1 | 1 | Done |  | 0 | 0
Figma Designing of Homepage | Design | Saketh | 3 | 2.5 | Delayed |  | 0.5 | 20
Database Schema | Design | Manasi | 3 | 1.5 | Done
Minutes of the Meeting | Documentation | Anshul | 2 | 2 | Done
Daily Standup - 19th Feb | Coordination | Anshul | 1 | 1 | Done
Daily Standup - 20th Feb | Coordination | Anshul | 1 | 1 | Done
Speech-to-text, text generation Design (input, processing models) | Design | Raghav | 3 | 1.5 | Delayed | Delayed due to midsem prep
Text-to-speech, visual Design (output models) | Design | Ishaan, Raghav | 3 | 2.5 | Done
Week 6 (February 24 - March 1) - Mid Semesters Week
Client Meeting - 24th February | Coordination | Anshul | 1 | 1 | Done |  | 0 | 0
Class Diagram and System-Level Design | Preparation | Raghav | 3 |  | Delayed | Delayed due to midsems
Figma Designing of Homepage | Design | Saketh | 1.5 | 2 | Done |  | -0.5 | 25
Avatar Preparation/ Rigging | Preparation | Ishaan | 2 |  | Delayed | Delayed due to midsems
Basic implementation of database | Preparation | Manasi | 2 |  | Delayed | Delayed due to midsems
Week 7 (March 2 - March 9)
Team Meet - 4th March | Coordination | Anshul | 1 | 1 | Done |  | 0 | 0
Being Front End Implementation - Landing Page | Development | Saketh, Raghav | 4 | 2.5 | Done |  | 1.5 | 60
Designing & Animating Avatar | Design | Ishaan | 3 | 2 | Delayed | Got sick | 1 | 50
Implementation of login/ signup (backend) | Development | Manasi | 3 |  | Delayed
Initial Database Design | Design | Anshul, Manasi | 2 | 2 | Done |  | 0 | 0
Finalise database design | Design | Manasi | 2 | 2 | Done |  | 0 | 0
Frontend Design | Frontend Design | Anshul, Raghav | 3 | 4 | Done |  | -1 | 25
Class Diagram and System-Level Design | Design | Raghav | 2 | 1.5 | Done |  | 0.5 | 33.3333
Team Meet - 8th March | Coordination | Manasi | 1 | 1 | Done |  | 0 | 0
Begin Design Document | Documentation | Anshul | 3 | 2 | Done
Client Meet - 9th March | Coordination | Manasi | 1 | 1 | Done |  | 0 | 0
Daily Standup - 4th March | Coordination | Anshul | 1 | 1 | Done |  | 0 | 0
Daily Standup - 5th March | Coordination | Anshul | 1 | 1 | Done |  | 0 | 0
Daily Standup - 6th March | Coordination | Manasi | 1 | 1 | Done |  | 0 | 0
Daily Standup - 8th March | Coordination | Manasi | 1 | 1 | Done |  | 0 | 0
Minutes of the Meeting | Documentation | Anshul | 1 | 1 | Done |  | 0 | 0
Week 8 (March 10 - March 16)
Team Meet - 10th March | Coordination | Manasi | 1 | 1 | Done |  | 0 | 0
Complete Design Document | Documentation | Anshul | 3 | 3 | Done |  | 0 | 0
Register, Login, Home page implementation | Development | Saketh | 5 | 6 | Done |  | -1 | 16.6667
Developing main avatar page | Development | Anshul | 4 | 3 | Done |  | 1 | 33.3333
Implement Rhubarb Lip Sync to generate visemes | Development | Ishaan | 1 | 0.5 | Done |  | 0.5 | 100
Integrate Rhubarb json file with animation | Development | Ishaan | 2 | 2 | Done |  | 0 | 0
Port animation to Three.js | Development | Ishaan | 2 | 3 | Done |  | -1 | 33.3333
Establish MongoDB Connection | Development | Raghav | 1 |  | Done
Integrate LLM pipeline with Backend API Endpoint | Development | Manasi | 4 | 5 | Done |  | -1 | 20
Setting up inital backend endpoints | Development | Raghav | 3 |  | Done
Team Meet - 15th march | Coordination | Saketh | 0.5 | 0.5 | Done |  | 0 | 0
R1 Presentation | Documentation | Saketh, Anshul | 2 |  | Delayed | Some design aspects needed to be reviewed
Establish Text-to-Speech Workflow | Development | Manasi | 2 | 2.5 | Done |  | -0.5 | 20
Establish Speech-to-Text Workflow | Development | Manasi | 2 | 2 | Done |  | 0 | 0
Set up authentication (frontend + backend) | Development | Raghav | 3 | 3 | Done |  | 0 | 0
Week 9 (March 17 - March 23)
Endpoint testing | Testing | Raghav | 4 |  | Ongoing
R1 Presentation | Documentation | Saketh, Anshul | 3 |  | Ongoing
Note on C5: SE: The person responsible for ensuring completion, not necessarily all the people doing it
Note on G5: swami: Insert your own comments
Note on H5: SE: This field is updated automatically